Planning Report

Level B — Deliverable D02

Workgroup G058

DP2 — University of Seville

May 2026

# Executive Summary

This report documents the planning, budget, and progress for the Level B deliverable (D02) of the Acme-Starters project, developed by workgroup G058 as part of the DP2 course at the University of Seville. The planning chapter presents the 86 tasks defined for D02 over the period 01 Apr 2026–08 May 2026, covering management, development, quality assurance, and other activities assigned across five team members. The total estimated effort amounts to 284.7 hours with an associated personnel budget of EUR 7,200.00, complemented by equipment amortisation of EUR 168.95, yielding a total expected budget of EUR 7,368.95. The budget chapter provides a detailed breakdown of expected and actual costs by role, along with deviation analysis. The progress chapter reports the Requirement Completion Rate (TCR) achieved by each team member across deliverables D01 and D02. All members achieved a TCR of 100% in both deliverables. No conflict resolution incidents were registered during the project period.

# Revision History

| Version | Date | Authors | Description |
| --- | --- | --- | --- |
| 1.0 | 07 May 2026 | All members | Initial release |

# 1. Introduction

The Acme-Starters project is developed by workgroup G058 as part of the DP2 (Diseño y Pruebas II) course at the E.T.S. de Ingeniería Informática, University of Seville. It manages projects, fundraising campaigns, inventions, audits, sponsorships, and promotional banners under a role-based access model supporting roles such as Manager, Consumer, Provider, Auditor, Inventor, Fundraiser, Sponsor, and Spokesperson.

The Level B deliverable (D02) covers the design, implementation, and documentation of intermediate-level features as specified in the course requirements. These include full domain modelling, CRUD operations for all Level B entities, business rule enforcement, publishing workflows, and dashboard functionalities. The deliverable also encompasses formal requirements documentation, UML analysis models, testing activities, and deployment operations.

The workgroup comprises five members operating under defined roles: one member acts as Manager responsible for project coordination, planning, and reporting; the remaining four members act primarily as Developers and Testers. Role assignments may overlap across tasks — for example, the Manager also performs development and testing tasks — and costs are charged at the rate corresponding to each specific task role.

This report is structured in five chapters: the Planning chapter lists all 86 D02 tasks with their assignments and time estimates; the Budget chapter analyses personnel and equipment costs; the Progress chapter evaluates individual performance via the TCR metric; and the Conclusions chapter summarises outcomes.

The D02 project period spans from 01 April 2026 to 08 May 2026 (37 calendar days). Task tracking is based on the official planning template provided by the course coordinators (Project-planing.xlsx). All tasks have been completed and actual hours recorded, showing minor deviations of up to ±1 hour with respect to estimates.

# 2. Planning

The table below lists all 86 tasks defined for D02. Columns show: task identifier, start and end dates, description, assigned member, role, and expected vs. actual hours. All tasks are completed.

| ID | Start | End | Description | Assignee | Role | Exp h | Act h |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T0001/M | 01 Apr 2026 | 04 Apr 2026 | Instantiate and share a planning document from the planning template provided, and plan on the tasks required to fulfil the Level B deliverable. | Student 4 | Manager | 3 | 3.5 |
| T0002/M | 01 Apr 2026 | 04 Apr 2026 | Set up the shared workgroup workspace for Level B and ensure all members have access. | Student 4 | Manager | 1 | 0 |
| T0003/M | 01 Apr 2026 | 04 Apr 2026 | Prepare a chartering report for Level B. Review and update the charter and risk analysis for Level B scope. | Student 4 | Manager | 2 | 1.5 |
| T0004/M | 01 Apr 2026 | 04 Apr 2026 | Initialise the Level B project branch in the workgroup repository at GitHub. | Student 4 | Manager | 1 | 0.5 |
| T0005/D | 01 Apr 2026 | 04 Apr 2026 | Prepare the foundations of the analysis report for Level B, including interpretation notes, open issues, and questions that require lecturer confirmation. | Student 4 | Developer | 2 | 2.5 |
| T0006/M | 01 Apr 2026 | 04 Apr 2026 | Ensure that every member understands the scope and goals of Level B and agrees to the common working methodology. | ALL | Manager | 1 | 1.5 |
| T0007/D | 01 Apr 2026 | 04 Apr 2026 | Adapt the starter project from Level C to Level B. Apply required infrastructure changes and update the project name to "Acme-Starters-B". | Student 1 | Developer | 2 | 3 |
| T0008/D | 01 Apr 2026 | 04 Apr 2026 | Create the sample data required to populate administrator accounts with credentials "administrator1/administrator1" and "administrator2/administrator2" for Level B. | Student 4 | Developer | 1 | 0 |
| T0009/D | 27 Apr 2026 | 04 May 2026 | Implement the complete Level B data model in one coherent task. Include Manager, Project, ProjectMembership, ProjectMember, AddBanner, sponsorships, audit reports, publication state, and intrinsic domain constraints. Apply feedback corrections: Project title as ValidHeader, publishMoment as Date, AddBanner slogan as ValidHeader, rename picture to targetPictureUrl, correct ProjectMembership cardinalities, and ensure Dashboard is not implemented as a persistent entity. | Student 1 | Developer | 12 | 12 |
| T0010/QA/T0009/D | 27 Apr 2026 | 04 May 2026 | Review the complete data model implementation. Check UML alignment, entity relationships, cardinalities, validations, publication-related intrinsic constraints, and that Dashboard is designed as a form object rather than as an entity. | Student 2 | Developer | 3 | 2 |
| T0011/D | 27 Apr 2026 | 04 May 2026 | Generate the Level B sample data in parallel with the data model task. Include managers, projects, published and unpublished composites, project members, inventions, campaigns, strategies, sponsorships, audit reports, add banners, duplicated ticker, fresh ticker, unpublished composite, component of unpublished composite, published composite, and component of published composite. | Student 3 | Developer | 8 | 7.5 |
| T0012/D/T0009/D/T0011/D | 27 Apr 2026 | 04 May 2026 | Integrate the complete data model with the generated sample data. Fix loading/profile issues, verify that sample data respects domain constraints, and ensure that the Level B application starts cleanly with the full dataset. | Student 4 | Developer | 5 | 5 |
| T0013/QA/T0012/D | 27 Apr 2026 | 04 May 2026 | Test the integrated data model and sample data together. Check that fixtures load correctly, publication states are consistent, duplicated and fresh ticker cases exist, and projects, components, sponsorships and audit reports are valid for later feature tests. | Student 5 | Developer | 3 | 2 |
| T0014/D | 27 Apr 2026 | 04 May 2026 | Implement FR-B01: any authenticated principal can acquire the Manager role and update the manager profile, including position, skills and executive flag. | Student 2 | Developer | 6 | 5.5 |
| T0015/QA/T0014/D | 27 Apr 2026 | 04 May 2026 | Test manager role acquisition and manager profile update with positive and negative cases. | Student 3 | Developer | 1 | 1.5 |
| T0016/D | 27 Apr 2026 | 04 May 2026 | Implement administrator AddBanner management: create, update, list, display and delete ad banners. Include slogan validation as ValidHeader, targetPictureUrl validation, administrator-only access, and non-intrusive rendering through ControllerAdvice or an equivalent shared UI mechanism. | Student 3 | Developer | 8 | 8 |
| T0017/QA/T0016/D | 27 Apr 2026 | 04 May 2026 | Test administrator ad banner management and verify that banners are rendered in the UI as little intrusively as possible. | Student 4 | Developer | 1 | 0.5 |
| T0018/D | 27 Apr 2026 | 04 May 2026 | Implement FR-B02 project management for managers: list, create, update and display own projects, including title, keywords, description, kick-off date, close-out date and publication state. Delete can be omitted if it is not required by the auditor focus. | Student 4 | Developer | 8 | 8 |
| T0019/QA/T0018/D | 27 Apr 2026 | 04 May 2026 | Test manager project management: list, create, update and display own projects, including ownership and access restrictions. | Student 5 | Developer | 1 | 1.5 |
| T0020/D | 27 Apr 2026 | 04 May 2026 | Implement project publication as a separate complex feature. Before publishing, verify that the project has at least one invention and valid kick-off/close-out dates with respect to component intervals. When a manager publishes a project, automatically publish its components and preserve transactional consistency. | Student 5 | Developer | 10 | 9 |
| T0021/QA/T0020/D | 27 Apr 2026 | 04 May 2026 | Test project publication preconditions, invalid publication attempts, cascade publication of components, and transactional consistency when publication fails. | Student 1 | Developer | 2 | 2.5 |
| T0022/D | 27 Apr 2026 | 04 May 2026 | Implement manager/project component management: add and manage inventions, campaigns and strategies associated with a project as a homogeneous feature package. | Student 1 | Developer | 8 | 8.5 |
| T0023/QA/T0022/D | 27 Apr 2026 | 04 May 2026 | Test adding and managing inventions, campaigns and strategies inside projects, including validation of component/project consistency. | Student 2 | Developer | 1 | 0.5 |
| T0024/D | 27 Apr 2026 | 04 May 2026 | Implement ProjectMembership management: list users who are not yet project members and allow managers to add inventors, spokespeople and fundraisers to projects. Do not include update, remove or ban behaviour. | Student 2 | Developer | 6 | 5.5 |
| T0025/QA/T0024/D | 27 Apr 2026 | 04 May 2026 | Test ProjectMembership creation, available-user listing, duplicate membership prevention, and role-specific membership constraints. | Student 3 | Developer | 1 | 2 |
| T0026/D | 27 Apr 2026 | 04 May 2026 | Implement FR-B09: sponsors can attach their published sponsorships to published projects only. Enforce the domain constraint that every sponsorship linked to a project requires the project to be published. | Student 3 | Developer | 6 | 5.5 |
| T0027/QA/T0026/D | 27 Apr 2026 | 04 May 2026 | Test sponsor attachment to published projects, blocking unpublished sponsorships, unpublished projects, wrong users and invalid IDs. | Student 4 | Developer | 1 | 0 |
| T0028/D | 27 Apr 2026 | 04 May 2026 | Implement FR-B10: auditors can attach their published audit reports to published projects only. Enforce the domain constraint that every audit report linked to a project requires the project to be published. | Student 4 | Developer | 6 | 5 |
| T0029/QA/T0028/D | 27 Apr 2026 | 04 May 2026 | Test auditor attachment to published projects, blocking unpublished audit reports, unpublished projects, wrong users and invalid IDs. | Student 5 | Developer | 1 | 1.5 |
| T0030/D | 27 Apr 2026 | 04 May 2026 | Implement the Manager Dashboard as a form object. Include total projects managed, deviation compared with the rest of managers, and min/max/average/standard deviation of project effort. If there is only one manager and deviation is undefined, show N/A instead of zero. | Student 5 | Developer | 8 | 8 |
| T0031/QA/T0030/D | 27 Apr 2026 | 04 May 2026 | Test dashboard calculations with deterministic datasets, including min, max, average, standard deviation, deviation against other managers, and the one-manager N/A case. | Student 1 | Developer | 2 | 2.5 |
| T0032/D | 27 Apr 2026 | 04 May 2026 | Implement cross-feature access-control hardening for unpublished project data. Ensure that only authorised managers and project members can access unpublished information and that non-members cannot access it through guessed URLs or tampered parameters. | Student 1 | Developer | 4 | 4.5 |
| T0033/QA/T0032/D | 27 Apr 2026 | 04 May 2026 | Test access-control hardening for unpublished project data using wrong user, wrong role, guessed URL, unpublished project ID and unpublished component ID cases. | Student 2 | Developer | 1 | 1 |
| T0034/QA/T0014/D | 04 May 2026 | 06 May 2026 | Produce and execute formal legal tests for manager role acquisition and manager profile update, including valid profile data, invalid profile constraints, repeated acquisition attempts and unauthorised access attempts. | Student 1 | Tester | 4 | 5 |
| T0035/QA/T0018/D | 04 May 2026 | 06 May 2026 | Produce and execute formal legal tests for project creation, update and display. Include valid and invalid titles, dates, keywords, ownership checks and unpublished visibility cases. | Student 2 | Tester | 4 | 4 |
| T0036/QA/T0020/D | 04 May 2026 | 06 May 2026 | Produce and execute formal legal and hacking tests for project publication. Validate publication preconditions and cascade publication. | Student 3 | Tester | 4 | 4 |
| T0037/QA/T0026/D | 04 May 2026 | 06 May 2026 | Produce and execute formal legal and hacking tests for sponsorship attachment to published projects. Include attempts with unpublished projects, unpublished sponsorships, wrong users, duplicated ticker and fresh ticker where relevant. | Student 4 | Tester | 4 | 4.5 |
| T0038/QA/T0028/D | 04 May 2026 | 06 May 2026 | Produce and execute formal legal and hacking tests for audit report attachment to published projects. Include attempts with unpublished projects, unpublished audit reports, wrong users and invalid IDs. | Student 5 | Tester | 4 | 4 |
| T0039/QA/T0030/D | 04 May 2026 | 06 May 2026 | Produce and execute formal tests for the manager dashboard, checking total projects, effort statistics, deviation against the rest of managers, standard deviation and N/A behaviour when deviation cannot be computed. | Student 1 | Tester | 4 | 4.5 |
| T0040/QA/T0016/D | 04 May 2026 | 06 May 2026 | Produce and execute formal tests for ad banner management and rendering, including ValidHeader slogan validation, targetPictureUrl validation, administrator-only access and non-intrusive display. | Student 2 | Tester | 4 | 4 |
| T0041/QA/T0024/D | 04 May 2026 | 06 May 2026 | Produce and execute formal tests for ProjectMembership management. Include listing users not yet assigned to the project, adding inventors, spokespeople and fundraisers, duplicate membership prevention and the absence of update/remove/ban actions. | Student 3 | Tester | 4 | 4.5 |
| T0042/QA/T0022/D | 04 May 2026 | 06 May 2026 | Produce and execute formal tests for adding and managing project components: inventions, campaigns and strategies. Include valid additions, invalid ownership, invalid publication state and project/component consistency. | Student 4 | Tester | 4 | 3 |
| T0043/QA/T0032/D | 04 May 2026 | 06 May 2026 | Produce and execute formal hacking tests for unpublished project access, including guessed URLs, wrong realm, wrong user, wrong action, unpublished composite and unpublished component. | Student 5 | Tester | 4 | 3.5 |
| T0044/QA/T0012/D | 04 May 2026 | 06 May 2026 | Validate the integrated model and sample dataset formally. Check that published/unpublished composites and components exist, that duplicated and fresh ticker cases are available, and that the dataset supports all required Level B feature tests. | Student 1 | Tester | 4 | 3.5 |
| T0045/QA/T0044/QA/T0012/D | 04 May 2026 | 06 May 2026 | Record and organise the Level B legal and hacking trace files, converting the tested scenarios into repeatable .legal and .hacking test cases for the formal test suite. | Student 2 | Tester | 4 | 3 |
| T0046/M | 04 May 2026 | 06 May 2026 | Write the planning report required by the customer's auditor, documenting the project planning, task breakdown, schedule, and resource allocation for Level B. | Student 4 | Manager | 2 | 1.5 |
| T0047/M | 04 May 2026 | 06 May 2026 | Write the Lint report required by the customer's auditor, documenting the results of static code analysis (linting) performed on the Level B codebase. | Student 4 | Manager | 2 | 1 |
| T0048/M | 04 May 2026 | 06 May 2026 | Write the testing report required by the customer's auditor, documenting the formal testing activities, test cases, results, and coverage for Level B. | Student 4 | Manager | 2 | 1.5 |
| T0049/D | 04 May 2026 | 07 May 2026 | Create deployment configuration for Level B application. | Student 2 | Operator | 2 | 2.5 |
| T0050/D | 04 May 2026 | 07 May 2026 | Deploy the Level B application to the target platform. | Student 2 | Operator | 1 | 0.5 |
| T0051/M | 04 May 2026 | 07 May 2026 | Monitor and keep the deployed Level B application healthy and running. | Student 2 | Operator | 4 | 3.5 |
| T0052/D | 04 May 2026 | 07 May 2026 | Package the Level B application and all required deliverables for submission. | Student 2 | Operator | 1 | 0.5 |
| T0053/R/T0052/D | 04 May 2026 | 07 May 2026 | Check the Level B deliverables against the requirements checklist. | Student 5 | Tester | 4 | 3.5 |
| T0054/R/T0052/D | 04 May 2026 | 07 May 2026 | Supervise the deliverable checking task and approve for submission. | Student 4 | Manager | 4 | 5 |
| T0055/M | 04 May 2026 | 08 May 2026 | Upload the Level B deliverables to the delivery centre. | Student 2 | Operator | 1 | 1.5 |
| T0056/R/T0055/M | 04 May 2026 | 08 May 2026 | Verify that the Level B deliverables have been correctly uploaded to the delivery centre. | Student 5 | Tester | 1 | 1 |
| T0057/O | 31 Mar 2026 | 31 Mar 2026 | Attend lecture. | ALL | Student | 1.8 | 1 |
| T0058/O | 03 Apr 2026 | 03 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 2.5 |
| T0059/O | 07 Apr 2026 | 07 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 1 |
| T0060/O | 10 Apr 2026 | 10 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 1.5 |
| T0061/O | 14 Apr 2026 | 14 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 3 |
| T0062/O | 17 Apr 2026 | 17 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 2 |
| T0063/O | 21 Apr 2026 | 21 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 2 |
| T0064/O | 24 Apr 2026 | 24 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 2 |
| T0065/O | 28 Apr 2026 | 28 Apr 2026 | Attend lecture. | ALL | Student | 1.8 | 2.5 |
| T0066/O | 25 Mar 2026 | 29 Apr 2026 | Study, read and understand the Level B lecture theory and course materials. | ALL | Student | 20 | 20.5 |
| T0067/O | 31 Mar 2026 | 31 Mar 2026 | Talk about the work done this week. | ALL | Student | 0.5 | 0 |
| T0068/O | 07 Apr 2026 | 07 Apr 2026 | Talk about the work done this week. | ALL | Student | 0.5 | 0 |
| T0069/O | 14 Apr 2026 | 14 Apr 2026 | Talk about the work done this week. | ALL | Student | 0.5 | 0 |
| T0070/O | 21 Apr 2026 | 21 Apr 2026 | Talk about the work done this week. | ALL | Student | 0.5 | 0 |
| T0071/O | 28 Apr 2026 | 28 Apr 2026 | Talk about the work done this week. | ALL | Student | 0.5 | 0 |
| T0072/D | 07 May 2026 | 08 May 2026 | Prepare the Level B analysis report and UML data model required by the auditor (MR-B01), including traceability between the structured requirements and the implemented solution. | Student 4 | Developer | 4 | 5 |
| T0073/M | 07 May 2026 | 08 May 2026 | Validate the analysis decisions and requirement ambiguities with a lecturer and document the confirmed resolutions in the analysis report (AR-B01). | Student 4 | Manager | 2 | 3 |
| T0074/M | 07 May 2026 | 08 May 2026 | Update the Level B planning records with progress tracking, budget estimates, and execution notes as required by the planning report (MR-B02, MR-B03). | Student 4 | Manager | 2 | 1.5 |
| T0075/QA/T0035/D | 07 May 2026 | 08 May 2026 | Create and execute formal hacking tests for unpublished project access, including guessed URLs, wrong realm, wrong user, wrong action, and tampered navigation attributes, ensuring intrusion alerts or equivalent protection responses. | Student 2 | Tester | 4 | 4.5 |
| T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Record and organise the Level B legal and hacking trace files, converting them into repeatable .legal and .hacking test cases for the formal test suite. | Student 3 | Tester | 4 | 4 |
| T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Replay the Level B formal test suite and review instruction coverage and the test case analyser results, identifying missing legal or hacking test cases where feasible. | Student 4 | Tester | 4 | 5 |
| T0078/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Review path coverage, loop cases, and mutation-oriented checks for the Level B test suite, documenting uncovered paths and justified exclusions where applicable. | Student 5 | Tester | 3 | 3 |
| T0079/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Check testing variability conditions for Level B, including English/Spanish rendering, simulated clock usage for temporal data, and simulated random seed control for repeatable execution. | Student 1 | Tester | 3 | 2.5 |
| T0080/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Replay the Level B test suite, import tester.trace into Excel, filter resource requests, compute per-feature execution times, and prepare the summary chart required for the performance analysis workflow. | Student 2 | Tester | 4 | 3.5 |
| T0081/QA/T0080/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 07 May 2026 | 08 May 2026 | Compute descriptive statistics and a 95% confidence interval for the Level B execution times using the performance data gathered from the formal test suite. | Student 3 | Tester | 3 | 3 |
| T0082/D | 07 May 2026 | 08 May 2026 | Profile the Most Inefficient Request of Level B using the recommended profiling tools and analyse whether the bottleneck is due to software or hardware behaviour. | Student 1 | Developer | 4 | 3.5 |
| T0083/D/T0082/D | 07 May 2026 | 08 May 2026 | Review the Level B queries and refactor them with indices where justified by the performance analysis, documenting the rationale and the affected entities or repositories. | Student 2 | Developer | 4 | 4 |
| T0084/QA/T0083/D | 07 May 2026 | 08 May 2026 | Collect new performance data after the refactoring, perform the hypothesis contrast or Z-test, and document whether the changes produced a statistically significant improvement. | Student 4 | Tester | 3 | 4 |
| T0085/D | 07 May 2026 | 08 May 2026 | Run lint and check-i18n on the Level B codebase, review the findings, and prepare the evidence to support the Lint report. | Student 1 | Developer | 2 | 2 |
| T0086/M | 07 May 2026 | 08 May 2026 | Write the Level B analysis report required by the auditor, including the requirement analysis, UML data model, documented ambiguities, confirmed lecturer decisions, and traceability notes. | Student 4 | Manager | 2 | 1.5 |

# 3. Budget

## 3.1 Personnel Costs

Personnel costs are calculated by multiplying hours by the role rate: Manager EUR 50/h · Developer EUR 25/h · Tester EUR 30/h · Operator EUR 30/h · Student EUR 0/h.

| Role | Exp. Hours | Act. Hours | Exp. Cost (EUR) | Act. Cost (EUR) |
| --- | --- | --- | --- | --- |
| Manager | 24.0 | 22.0 | 1,200.00 | 1,100.00 |
| Developer | 132.0 | 129.5 | 3,300.00 | 3,237.50 |
| Tester | 81.0 | 81.5 | 2,430.00 | 2,445.00 |
| Operator | 9.0 | 8.5 | 270.00 | 255.00 |
| Student | 38.7 | 38.0 | 0.00 | 0.00 |
| TOTAL | 284.7 | 279.5 | 7,200.00 | 7,037.50 |

## 3.2 Equipment Amortisation

The workgroup uses 5 laptop computers, each with an approximate acquisition cost of EUR 1,000.00. Total equipment cost: EUR 5,000.00. Applying straight-line amortisation over 3 years, the annual charge is EUR 1,666.67/year. For the D02 period of 37 calendar days (01 Apr 2026 to 08 May 2026), the proportional charge amounts to EUR 694.06.

| Equipment | Units | Unit Cost (EUR) | Annual Amort. (EUR) | D02 Amort. (37d, EUR) |
| --- | --- | --- | --- | --- |
| Laptop computer | 5 | 1,000.00 | 1,666.67 | 168.95 |

## 3.3 Total Budget Summary

| Item | Expected (EUR) | Actual (EUR) |
| --- | --- | --- |
| Personnel costs | 7,200.00 | 7,037.50 |
| Equipment amortisation (37 days) | 168.95 | 168.95 |
| GRAND TOTAL | 7,368.95 | 7,206.45 |

## 3.4 Deviation Analysis

The overall budget deviation for D02 is EUR -162.50 (-2.1% relative to the expected total). Individual tasks show minor variations of up to ±1 hour between planned and actual duration, reflecting normal estimation uncertainty at the task level. Across 86 tasks these small differences partially offset each other, resulting in an actual personnel cost of EUR 7,037.50 versus the expected EUR 7,200.00. The equipment amortisation charge is identical in both scenarios, as it depends on calendar duration rather than working hours. No extraordinary deviations or scope changes were recorded during D02.

# 4. Progress

The Requirement Completion Rate (TCR) measures the proportion of reviewed requirements that were accepted: TCR = (accepted / reviewed) × 100. The table below shows the TCR achieved by each team member for D01 and D02.

| Member | D01 — TCR (%) | D02 — TCR (%) | Assessment |
| --- | --- | --- | --- |
| Student 1 | 100 % | 100 % | Good |
| Student 2 | 100 % | 100 % | Good |
| Student 3 | 100 % | 100 % | Good |
| Student 4 | 100 % | 100 % | Good |
| Student 5 | 100 % | 100 % | Good |

## 4.1 Rewards and Admonishments

No performance rewards or admonishments were issued during D01 or D02. All team members met or exceeded the minimum TCR threshold of 75% defined in the Chartering Report. No conflicts requiring formal resolution procedures were registered during the project period.

## 4.2 Dismissal Conditions

No dismissal conditions were triggered during the project. All team members remained active and contributing throughout both deliverable periods in accordance with the work agreements established in the Chartering Report.

# 5. Conclusions

This planning report provides a comprehensive view of the planning, budget, and progress of workgroup G058 for the Level B deliverable (D02) of the Acme-Starters project. A total of 86 tasks were defined and tracked across five team members over the period 01 Apr 2026–08 May 2026, covering management, development, quality assurance, and other activities. The total expected effort of 284.7 hours translates to a personnel budget of EUR 7,200.00, plus EUR168.95 in equipment amortisation, for a total expected budget of EUR 7,368.95.

From a progress perspective, all team members achieved a Requirement Completion Rate of 100% for both D01 and D02, meeting the performance indicators established in the Chartering Report. No conflict resolution incidents, rewards, or admonishments were recorded. The team maintained a stable and collaborative working environment throughout both deliverable cycles.

Task-level deviations were minimal, with actual hours differing by at most one hour from estimates. This reflects accurate initial planning and consistent execution by the team throughout the D02 period.

# 6. Bibliography

[1] DP2 Course Staff. On your reports. University of Seville, 2025–2026.

[2] DP2 Course Staff. Project Planning Template (Project-planing2.xlsx). University of Seville, 2025–2026.

[3] Workgroup G058. Chartering Report — Level B. University of Seville, 2026.