## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 8720
|  | Actual: | 8002.5
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 4 | Manager | Other (Describe) |  | 2026-01-29 | 2026-01-30 | Completed | 1 | 1 | 50 | 50 | Setup the workgroup.
2 | T0002/M | Management | Student 4 | Manager | Write report |  | 2026-01-29 | 2026-01-30 | Completed | 2 | 2 | 100 | 100 | Prepare a chartering report.
3 | T0003/M | Management | Student 4 | Manager | Make plans |  | 2026-01-29 | 2026-01-31 | Completed | 3 | 4 | 150 | 200 | Instantiate and share a planning document from the planning template provid-ed, and plan on the tasks required to fulfil this deliverable.
4 | T0004/D | Development | ALL | Developer | Other (Describe) |  | 2026-01-30 | 2026-01-31 | Completed | 5 | 5 | 125 | 125 | Install and initialise the workspace.
5 | T0005/M | Management | Student 4 | Manager | Initialise repository |  | 2026-01-31 | 2026-02-01 | Completed | 1 | 4 | 50 | 200 | Initialise the workgroup repository at GitHub.
6 | T0006/D | Development | Student 1 | Developer | Customise the starter |  | 2026-02-02 | 2026-02-03 | Completed | 2 | 1.5 | 50 | 37.5 | Instantiate the starter project “Hello-World” as “Acme-Starters-C”. The corpo-rate colours, banners, logos, and other such stuff is up to the workgroup.
7 | T0007/O | Other | ALL | Student | Study and train |  | 2026-02-02 | 2026-03-20 | Completed | 20 | 20 | 0 | 0 | Study, read and understand the lectures teory.
8 | T0008/O | Other | ALL | Student | Attend work meeting |  | 2026-02-02 15:00 | 2026-02-02 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
9 | T0009/O | Other | ALL | Student | Attend lecture |  | 2026-02-02 15:30 | 2026-02-02 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
10 | T0010/D | Development | Student 2 | Developer | Other (Describe) |  | 2026-02-04 | 2026-02-05 | Completed | 1 | 3 | 25 | 75 | Create the sample data required to create two administrator accounts with cre-dentials “administrator1/administrator1” and “administrator2/administrator2”.
11 | T0011/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-04 | 2026-02-05 | Completed | 3 | 2 | 75 | 50 | Implement the constraints that are sketched in file “Model-CG.ufx”.
12 | T0012/O | Other | ALL | Student | Attend lecture |  | 2026-02-05 15:30 | 2026-02-05 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
13 | T0013/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 9 | 250 | 225 | Implement the data model that is sketched in file “Model-C01.uxf”.
14 | T0014/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 10 | 250 | 250 | Implement the data model that is sketched in file “Model-C02.uxf”.
15 | T0015/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 7 | 250 | 175 | Implement the data model that is sketched in file “Model-C03.uxf”.
16 | T0016/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 9 | 250 | 225 | Implement the data model that is sketched in file “Model-C04.uxf”.
17 | T0017/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 5 | 250 | 125 | Implement the data model that is sketched in file “Model-C05.uxf”.
18 | T0018/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
19 | T0019/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
20 | T0020/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
21 | T0021/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
22 | T0022/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
23 | T0023/O | Other | ALL | Student | Attend work meeting |  | 2026-02-09 15:00 | 2026-02-09 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
24 | T0024/O | Other | ALL | Student | Attend lecture |  | 2026-02-09 15:30 | 2026-02-09 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
25 | T0025/O | Other | ALL | Student | Attend lecture |  | 2026-02-12 15:30 | 2026-02-12 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
26 | T0026/O | Other | ALL | Student | Attend work meeting |  | 2026-02-16 15:00 | 2026-02-16 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
27 | T0027/O | Other | ALL | Student | Attend lecture |  | 2026-02-16 15:30 | 2026-02-16 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
28 | T0028/O | Other | ALL | Student | Attend lecture |  | 2026-02-19 15:30 | 2026-02-19 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
29 | T0029/QA/T0013/D | QA | Student 1 | Tester | Test feature formally | T0013/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role inventor and credentials “inventori/inventori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
30 | T0030/QA/T0014/D | QA | Student 2 | Tester | Test feature formally | T0014/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role spokesperson and credentials “spokespersoni/spokespersoni”, where “i” ranges in interval one up to three. The last user account must not have any associ-ated data, but the profile data required to create the user account itself and the cor-responding role.
31 | T0031/QA/T0015/D | QA | Student 3 | Tester | Test feature formally | T0015/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role fundraiser and credentials “fundraiseri/fundraiseri”, where “i” ranges in in-terval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
32 | T0032/QA/T0016/D | QA | Student 4 | Tester | Test feature formally | T0016/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 6 | 120 | 180 | Produce sample data to test your requirements. There must be three user accounts with role sponsor and credentials “sponsori/sponsori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
33 | T0033/QA/T0017/D | QA | Student 5 | Tester | Test feature formally | T0017/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role auditor and credentials “auditori/auditori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the pro-file data required to create the user account itself and the corresponding role.
34 | T0034/O | Other | ALL | Student | Attend work meeting |  | 2026-02-23 15:00 | 2026-02-23 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
35 | T0035/O | Other | ALL | Student | Attend lecture |  | 2026-02-23 15:30 | 2026-02-23 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
36 | T0036/O | Other | ALL | Student | Attend lecture |  | 2026-02-26 15:30 | 2026-02-26 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
37 | T0037/O | Other | ALL | Student | Attend work meeting |  | 2026-03-02 15:00 | 2026-03-02 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
38 | T0038/O | Other | ALL | Student | Attend lecture |  | 2026-03-02 15:30 | 2026-03-02 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
39 | T0039/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 8 | 200 | 200 | List and display the inventions in the system as long as they have been published. The principal must be able to navigate to their parts and display them. He or she must be able to see the profile of the corresponding inventor.
40 | T0040/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 8 | 200 | 200 | List and display the campaigns in the system as long as they have been published. The principal must be able to navigate to their milestones and display them. He or she must be able to see the profile of the corresponding spokesperson.
41 | T0041/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 7 | 200 | 175 | List and display the strategies in the system as long as they have been published. The principal must be able to navigate to their tactics and display them. He or she must be able to see the profile of the corresponding fundraiser.
42 | T0042/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 5 | 200 | 125 | List and display the sponsorships in the system as long as they have been published. The principal must be able to navigate to their donations and display them. He or she must be able to see the profile of the corresponding sponsor.
43 | T0043/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 6 | 200 | 150 | List and display the audit reports in the system as long as they have been published. The principal must be able to navigate to their audit sections and display them. He or she must be able to see the profile of the corresponding auditor.
44 | T0044/O | Other | ALL | Student | Attend lecture |  | 2026-03-05 15:30 | 2026-03-05 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
45 | T0045/QA/T0017/D | QA | Student 2 | Developer | Test feature informally | T0017/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
46 | T0046/QA/T0039/D | QA | Student 3 | Developer | Test feature informally | T0039/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
47 | T0047/QA/T0040/D | QA | Student 4 | Developer | Test feature informally | T0040/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
48 | T0048/QA/T0041/D | QA | Student 5 | Developer | Test feature informally | T0041/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
49 | T0049/QA/T0042/D | QA | Student 1 | Developer | Test feature informally | T0042/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
50 | T0050/O | Other | ALL | Student | Attend work meeting |  | 2026-03-09 15:00 | 2026-03-09 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
51 | T0051/O | Other | ALL | Student | Attend lecture |  | 2026-03-09 15:30 | 2026-03-09 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
52 | T0052/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role inventor as long as he or she does not have that role yet. • Update the corresponding role profile.
53 | T0053/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role spokesperson as long as he or she does not have that role yet. • Update the corresponding role profile.
54 | T0054/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 2 | 100 | 50 | Any authenticated principal must be able to: • Acquire role fundraiser as long as he or she does not have that role yet. • Update the corresponding role profile.
55 | T0055/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role sponsor as long as he or she does not have that role yet. • Update the corresponding role profile.
56 | T0056/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 3 | 100 | 75 | Any authenticated principal must be able to: • Acquire role auditor as long as he or she does not have that role yet. • Update the corresponding role profile.
57 | T0057/O | Other | ALL | Student | Attend lecture |  | 2026-03-12 15:30 | 2026-03-12 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
58 | T0058/QA/T0052/D | QA | Student 2 | Developer | Test feature informally | T0052/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
59 | T0059/QA/T0053/D | QA | Student 3 | Developer | Test feature informally | T0053/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
60 | T0060/QA/T0054/D | QA | Student 4 | Developer | Test feature informally | T0054/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
61 | T0061/QA/T0055/D | QA | Student 5 | Developer | Test feature informally | T0055/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
62 | T0062/QA/T0056/D | QA | Student 1 | Developer | Test feature informally | T0056/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
63 | T0063/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 14 | 8 | 350 | 200 | A principal with role inventor must be able to: • Manage his or her inventions, which involves creating, updating, or deleting them and their corresponding parts.
64 | T0064/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role spokesperson must be able to: • Manage his or her campaigns, which involves creating, updating, or deleting them and their corresponding milestones.
65 | T0065/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role fundraiser must be able to: • Manage his or her strategies, which involves creating, updating, and deleting them and their corresponding tactics.
66 | T0066/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role sponsor must be able to: • Manage his or her sponsorships, which involves creating, updating, or deleting them and their corresponding donations.
67 | T0067/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role auditor must be able to: • Manage his or her audit reports, which involves creating, updating, or deleting them and their corresponding audit sections.
68 | T0068/QA/T0063/D | QA | Student 2 | Developer | Test feature informally | T0063/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
69 | T0069/QA/T0064/D | QA | Student 3 | Developer | Test feature informally | T0064/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
70 | T0070/QA/T0065/D | QA | Student 4 | Developer | Test feature informally | T0065/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
71 | T0071/QA/T0066/D | QA | Student 5 | Developer | Test feature informally | T0066/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
72 | T0072/QA/T0067/D | QA | Student 1 | Developer | Test feature informally | T0067/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
73 | T0073/O | Other | ALL | Student | Attend work meeting |  | 2026-03-16 15:00 | 2026-03-16 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
74 | T0074/O | Other | ALL | Student | Attend lecture |  | 2026-03-16 15:30 | 2026-03-16 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
75 | T0075/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 8 | 4 | 200 | 100 | A principal with role inventor must be able to: • Publish an invention, which prevents it from being updated or deleted. Publishing them implies that their corresponding parts are published automatically, which also prevents them from being updated or deleted.
76 | T0076/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 |  | 200 |  | A principal with role spokesperson must be able to: • Publish a campaign, which prevents it from being updated or deleted. Publishing them implies that their corresponding milestones are published automatically, which also prevents them from being updated or deleted.
77 | T0077/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 4 | 200 | 100 | A principal with role fundraiser must be able to: • Publish a strategy, which prevents it from being updated or deleted. Publishing them implies that their corresponding tactics are published automatically, which al-so prevents them from being updated or deleted.
78 | T0078/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 8 | 200 | 200 | A principal with role sponsor must be able to: • Publish a sponsorship, which prevents it from being updated or deleted. Publishing them implies that their corresponding donations are published automatically, which also prevents them from being updated or deleted.
79 | T0079/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 7 | 200 | 175 | A principal with role auditor must be able to: • Publish an audit report, which prevents it from being updated or deleted. Publish-ing them implies that their corresponding audit sections are published automatical-ly, which also prevents them from being updated or deleted.
80 | T0080/QA/T0075/D | QA | Student 2 | Developer | Test feature informally | T0075/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
81 | T0081/QA/T0076/D | QA | Student 3 | Developer | Test feature informally | T0076/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
82 | T0082/QA/T0077/D | QA | Student 4 | Developer | Test feature informally | T0077/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
83 | T0083/QA/T0078/D | QA | Student 5 | Developer | Test feature informally | T0078/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
84 | T0084/QA/T0079/D | QA | Student 1 | Developer | Test feature informally | T0079/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
85 | T0085/QA/T0018/D | QA | Student 2 | Developer | Test feature informally | T0018/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
86 | T0086/QA/T0019/D | QA | Student 3 | Developer | Test feature informally | T0019/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
87 | T0087/QA/T0020/D | QA | Student 4 | Developer | Test feature informally | T0020/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
88 | T0088/QA/T0021/D | QA | Student 5 | Developer | Test feature informally | T0021/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
89 | T0089/QA/T0022/D | QA | Student 1 | Developer | Test feature informally | T0022/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
90 | T0090/D | Development | Student 2 | Operator | Prepare dep. platf. |  | 2026-03-18 | 2026-03-19 | Completed | 2 | 2 | 60 | 60 | Create deployment configuration.
91 | T0091/D | Development | Student 2 | Operator | Deploy application |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Deploy the application.
92 | T0092/M | Management | Student 2 | Operator | Keep application running | T0091/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 4 | 120 | 120 | Keep it healthy and running.
93 | T0093/D | Development | Student 2 | Operator | Package deliverable |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Package the application for the delivery.
94 | T0094/R/T0093/D | Revision | Student 5 | Tester | Check deliverable | T0093/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 6 | 120 | 180 | Check the deriveables.
95 | T0095/R/T0094/R/T0093/D | Revision | Student 4 | Manager | Supervise task | T0094/R/T0093/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 7 | 200 | 350 | Check the deriveables.
96 | T0096/M | Management | Student 2 | Operator | Upload deliverable |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Upload the deriveables to the delivery center.
97 | T0097/R/T0096/M | Revision | Student 5 | Tester | Check task | T0096/M | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Check the derivery.
98 | T0098/O | Other | ALL | Student | Attend lecture |  | 2026-03-19 15:30 | 2026-03-19 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
99
100
101

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 4 | Manager | Make plans |  | 2025-01-04 | 2025-04-04 | Completed | 3 | 4 | EUR 150,00 |  | Instantiate and share a planning document from the planning template provided, and plan on the tasks required to fulfil the Level B deliverable.
2 | T0002/M | Management | Student 4 | Manager | Other (Describe) |  | 2025-01-04 | 2025-04-04 | Completed | 1 | 2 | EUR 50,00 |  | Set up the shared workgroup workspace for Level B and ensure all members have access.
3 | T0003/M | Management | Student 4 | Manager | Write report |  | 2025-01-04 | 2025-04-04 | Completed | 2 | 3 | EUR 100,00 |  | Prepare a chartering report for Level B. Review and update the charter and risk analysis for Level B scope.
4 | T0004/M | Management | Student 4 | Manager | Initialise repository |  | 2025-01-04 | 2025-04-04 | Completed | 1 | 1 | EUR 50,00 |  | Initialise the Level B project branch in the workgroup repository at GitHub.
5 | T0005/D | Development | Student 4 | Developer | Other (Describe) |  | 2025-01-04 | 2025-04-04 | Completed | 2 | 3 | EUR 50,00 |  | Prepare the foundations of the analysis report for Level B, including interpretation notes, open issues, and questions that require lecturer confirmation.
6 | T0006/M | Management | ALL | Manager | Other (Describe) |  | 2025-01-04 | 2025-04-04 | Completed | 1 | 1 | EUR 50,00 |  | Ensure that every member understands the scope and goals of Level B and agrees to the common working methodology.
7 | T0007/D | Development | Student 1 | Developer | Customise the starter |  | 2025-01-04 | 2025-04-04 | Completed | 2 | 1 | EUR 50,00 |  | Adapt the starter project from Level C to Level B. Apply required infrastructure changes and update the project name to "Acme-Starters-B".
8 | T0008/D | Development | Student 4 | Developer | Create dev. config. |  | 2025-01-04 | 2025-04-04 | Completed | 1 | 1 | EUR 25,00 |  | Create the sample data required to populate administrator accounts with credentials "administrator1/administrator1" and "administrator2/administrator2" for Level B.
9 | T0009/D | Development | Student 1 | Developer | Implement feature |  | 04/27/2026 00:00 | 2026-04-05 | Completed | 12 |  | EUR 300,00 |  | Implement the complete Level B data model in one coherent task. Include Manager, Project, ProjectMembership, ProjectMember, AddBanner, sponsorships, audit reports, publication state, and intrinsic domain constraints. Apply feedback corrections: Project title as ValidHeader, publishMoment as Date, AddBanner slogan as ValidHeader, rename picture to targetPictureUrl, correct ProjectMembership cardinalities, and ensure Dashboard is not implemented as a persistent entity.
10 | T0010/QA/T0009/D | QA | Student 2 | Developer | Test feature informally | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 3 |  | EUR 75,00 |  | Review the complete data model implementation. Check UML alignment, entity relationships, cardinalities, validations, publication-related intrinsic constraints, and that Dashboard is designed as a form object rather than as an entity.
11 | T0011/D | Development | Student 3 | Developer | Create dev. config. |  | 04/27/2026 00:00 | 2026-04-05 | Completed | 8 |  | EUR 200,00 |  | Generate the Level B sample data in parallel with the data model task. Include managers, projects, published and unpublished composites, project members, inventions, campaigns, strategies, sponsorships, audit reports, add banners, duplicated ticker, fresh ticker, unpublished composite, component of unpublished composite, published composite, and component of published composite.
12 | T0012/D/T0009/D/T0011/D | Development | Student 4 | Developer | Other (Describe) | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 5 |  | EUR 125,00 |  | Integrate the complete data model with the generated sample data. Fix loading/profile issues, verify that sample data respects domain constraints, and ensure that the Level B application starts cleanly with the full dataset.
13 | T0013/QA/T0012/D | QA | Student 5 | Developer | Test feature informally | T0012/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 3 |  | EUR 75,00 |  | Test the integrated data model and sample data together. Check that fixtures load correctly, publication states are consistent, duplicated and fresh ticker cases exist, and projects, components, sponsorships and audit reports are valid for later feature tests.
14 | T0014/D | Development | Student 2 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 6 |  | EUR 150,00 |  | Implement FR-B01: any authenticated principal can acquire the Manager role and update the manager profile, including position, skills and executive flag.
15 | T0015/QA/T0014/D | QA | Student 3 | Developer | Test feature informally | T0014/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test manager role acquisition and manager profile update with positive and negative cases.
16 | T0016/D | Development | Student 3 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 8 |  | EUR 200,00 |  | Implement administrator AddBanner management: create, update, list, display and delete ad banners. Include slogan validation as ValidHeader, targetPictureUrl validation, administrator-only access, and non-intrusive rendering through ControllerAdvice or an equivalent shared UI mechanism.
17 | T0017/QA/T0016/D | QA | Student 4 | Developer | Test feature informally | T0016/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test administrator ad banner management and verify that banners are rendered in the UI as little intrusively as possible.
18 | T0018/D | Development | Student 4 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 8 |  | EUR 200,00 |  | Implement FR-B02 project management for managers: list, create, update and display own projects, including title, keywords, description, kick-off date, close-out date and publication state. Delete can be omitted if it is not required by the auditor focus.
19 | T0019/QA/T0018/D | QA | Student 5 | Developer | Test feature informally | T0018/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test manager project management: list, create, update and display own projects, including ownership and access restrictions.
20 | T0020/D | Development | Student 5 | Developer | Implement feature | T0018/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 10 |  | EUR 250,00 |  | Implement project publication as a separate complex feature. Before publishing, verify that the project has at least one invention and valid kick-off/close-out dates with respect to component intervals. When a manager publishes a project, automatically publish its components and preserve transactional consistency.
21 | T0021/QA/T0020/D | QA | Student 1 | Developer | Test feature informally | T0020/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 2 |  | EUR 50,00 |  | Test project publication preconditions, invalid publication attempts, cascade publication of components, and transactional consistency when publication fails.
22 | T0022/D | Development | Student 1 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 8 |  | EUR 200,00 |  | Implement manager/project component management: add and manage inventions, campaigns and strategies associated with a project as a homogeneous feature package.
23 | T0023/QA/T0022/D | QA | Student 2 | Developer | Test feature informally | T0022/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test adding and managing inventions, campaigns and strategies inside projects, including validation of component/project consistency.
24 | T0024/D | Development | Student 2 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 6 |  | EUR 150,00 |  | Implement ProjectMembership management: list users who are not yet project members and allow managers to add inventors, spokespeople and fundraisers to projects. Do not include update, remove or ban behaviour.
25 | T0025/QA/T0024/D | QA | Student 3 | Developer | Test feature informally | T0024/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test ProjectMembership creation, available-user listing, duplicate membership prevention, and role-specific membership constraints.
26 | T0026/D | Development | Student 3 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 6 |  | EUR 150,00 |  | Implement FR-B09: sponsors can attach their published sponsorships to published projects only. Enforce the domain constraint that every sponsorship linked to a project requires the project to be published.
27 | T0027/QA/T0026/D | QA | Student 4 | Developer | Test feature informally | T0026/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test sponsor attachment to published projects, blocking unpublished sponsorships, unpublished projects, wrong users and invalid IDs.
28 | T0028/D | Development | Student 4 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 6 |  | EUR 150,00 |  | Implement FR-B10: auditors can attach their published audit reports to published projects only. Enforce the domain constraint that every audit report linked to a project requires the project to be published.
29 | T0029/QA/T0028/D | QA | Student 5 | Developer | Test feature informally | T0028/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test auditor attachment to published projects, blocking unpublished audit reports, unpublished projects, wrong users and invalid IDs.
30 | T0030/D | Development | Student 5 | Developer | Implement feature | T0009/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 8 |  | EUR 200,00 |  | Implement the Manager Dashboard as a form object. Include total projects managed, deviation compared with the rest of managers, and min/max/average/standard deviation of project effort. If there is only one manager and deviation is undefined, show N/A instead of zero.
31 | T0031/QA/T0030/D | QA | Student 1 | Developer | Test feature informally | T0030/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 2 |  | EUR 50,00 |  | Test dashboard calculations with deterministic datasets, including min, max, average, standard deviation, deviation against other managers, and the one-manager N/A case.
32 | T0032/D | Development | Student 1 | Developer | Implement feature | T0020/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 4 |  | EUR 100,00 |  | Implement cross-feature access-control hardening for unpublished project data. Ensure that only authorised managers and project members can access unpublished information and that non-members cannot access it through guessed URLs or tampered parameters.
33 | T0033/QA/T0032/D | QA | Student 2 | Developer | Test feature informally | T0032/D | 04/27/2026 00:00 | 2026-04-05 | Completed | 1 |  | EUR 25,00 |  | Test access-control hardening for unpublished project data using wrong user, wrong role, guessed URL, unpublished project ID and unpublished component ID cases.
34 | T0034/QA/T0014/D | QA | Student 1 | Tester | Test feature formally | T0014/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal legal tests for manager role acquisition and manager profile update, including valid profile data, invalid profile constraints, repeated acquisition attempts and unauthorised access attempts.
35 | T0035/QA/T0018/D | QA | Student 2 | Tester | Test feature formally | T0018/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal legal tests for project creation, update and display. Include valid and invalid titles, dates, keywords, ownership checks and unpublished visibility cases.
36 | T0036/QA/T0020/D | QA | Student 3 | Tester | Test feature formally | T0020/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal legal and hacking tests for project publication. Validate publication preconditions and cascade publication.
37 | T0037/QA/T0026/D | QA | Student 4 | Tester | Test feature formally | T0026/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal legal and hacking tests for sponsorship attachment to published projects. Include attempts with unpublished projects, unpublished sponsorships, wrong users, duplicated ticker and fresh ticker where relevant.
38 | T0038/QA/T0028/D | QA | Student 5 | Tester | Test feature formally | T0028/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal legal and hacking tests for audit report attachment to published projects. Include attempts with unpublished projects, unpublished audit reports, wrong users and invalid IDs.
39 | T0039/QA/T0030/D | QA | Student 1 | Tester | Test feature formally | T0030/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal tests for the manager dashboard, checking total projects, effort statistics, deviation against the rest of managers, standard deviation and N/A behaviour when deviation cannot be computed.
40 | T0040/QA/T0016/D | QA | Student 2 | Tester | Test feature formally | T0016/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal tests for ad banner management and rendering, including ValidHeader slogan validation, targetPictureUrl validation, administrator-only access and non-intrusive display.
41 | T0041/QA/T0024/D | QA | Student 3 | Tester | Test feature formally | T0024/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal tests for ProjectMembership management. Include listing users not yet assigned to the project, adding inventors, spokespeople and fundraisers, duplicate membership prevention and the absence of update/remove/ban actions.
42 | T0042/QA/T0022/D | QA | Student 4 | Tester | Test feature formally | T0022/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal tests for adding and managing project components: inventions, campaigns and strategies. Include valid additions, invalid ownership, invalid publication state and project/component consistency.
43 | T0043/QA/T0032/D | QA | Student 5 | Tester | Test feature formally | T0032/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Produce and execute formal hacking tests for unpublished project access, including guessed URLs, wrong realm, wrong user, wrong action, unpublished composite and unpublished component.
44 | T0044/QA/T0012/D | QA | Student 1 | Tester | Test feature formally | T0012/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Validate the integrated model and sample dataset formally. Check that published/unpublished composites and components exist, that duplicated and fresh ticker cases are available, and that the dataset supports all required Level B feature tests.
45 | T0045/QA/T0044/QA/T0012/D | QA | Student 2 | Tester | Test feature formally | T0044/QA/T0012/D | 2026-04-05 | 2026-06-05 | Completed | 4 |  | EUR 120,00 |  | Record and organise the Level B legal and hacking trace files, converting the tested scenarios into repeatable .legal and .hacking test cases for the formal test suite.
46 | T0046/M | Management | Student 4 | Manager | Write report |  | 2026-04-05 | 2026-06-05 | Completed | 2 |  | EUR 100,00 |  | Write the planning report required by the customer's auditor, documenting the project planning, task breakdown, schedule, and resource allocation for Level B.
47 | T0047/M | Management | Student 4 | Manager | Write report |  | 2026-04-05 | 2026-06-05 | Completed | 2 |  | EUR 100,00 |  | Write the Lint report required by the customer's auditor, documenting the results of static code analysis (linting) performed on the Level B codebase.
48 | T0048/M | Management | Student 4 | Manager | Write report |  | 2026-04-05 | 2026-06-05 | Completed | 2 |  | EUR 100,00 |  | Write the testing report required by the customer's auditor, documenting the formal testing activities, test cases, results, and coverage for Level B.
49 | T0049/D | Development | Student 2 | Operator | Prepare dep. platf. |  | 2026-06-05 | 2026-07-05 | Completed | 2 |  | EUR 60,00 |  | Create deployment configuration for Level B application.
50 | T0050/D | Development | Student 2 | Operator | Deploy application | T0049/D | 2026-06-05 | 2026-07-05 | Completed | 1 |  | EUR 30,00 |  | Deploy the Level B application to the target platform.
51 | T0051/M | Management | Student 2 | Operator | Keep application running | T0050/D | 2026-06-05 | 2026-07-05 | Completed | 4 |  | EUR 120,00 |  | Monitor and keep the deployed Level B application healthy and running.
52 | T0052/D | Development | Student 2 | Operator | Package deliverable |  | 2026-06-05 | 2026-07-05 | Completed | 1 |  | EUR 30,00 |  | Package the Level B application and all required deliverables for submission.
53 | T0053/R/T0052/D | Revision | Student 5 | Tester | Check deliverable | T0052/D | 2026-06-05 | 2026-07-05 | Completed | 4 |  | EUR 120,00 |  | Check the Level B deliverables against the requirements checklist.
54 | T0054/R/T0052/D | Revision | Student 4 | Manager | Supervise task | T0052/D | 2026-06-05 | 2026-07-05 | Completed | 4 |  | EUR 200,00 |  | Supervise the deliverable checking task and approve for submission.
55 | T0055/M | Management | Student 2 | Operator | Upload deliverable | T0054/R/T0052/D | 2026-07-05 | 2026-08-05 | Completed | 1 |  | EUR 30,00 |  | Upload the Level B deliverables to the delivery centre.
56 | T0056/R/T0055/M | Revision | Student 5 | Tester | Check task | T0055/M | 2026-07-05 | 2026-08-05 | Completed | 1 |  | EUR 30,00 |  | Verify that the Level B deliverables have been correctly uploaded to the delivery centre.
57 | T0057/O | Other | ALL | Student | Attend lecture |  | 3/31/2026 15:30 | 3/31/2026 17:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
58 | T0058/O | Other | ALL | Student | Attend lecture |  | 2026-03-04 17:30 | 2026-03-04 19:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
59 | T0059/O | Other | ALL | Student | Attend lecture |  | 2026-07-04 15:30 | 2026-07-04 17:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
60 | T0060/O | Other | ALL | Student | Attend lecture |  | 2026-10-04 17:30 | 2026-10-04 19:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
61 | T0061/O | Other | ALL | Student | Attend lecture |  | 4/14/2026 15:30 | 4/14/2026 17:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
62 | T0062/O | Other | ALL | Student | Attend lecture |  | 4/17/2026 17:30 | 4/17/2026 19:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
63 | T0063/O | Other | ALL | Student | Attend lecture |  | 4/21/2026 15:30 | 4/21/2026 17:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
64 | T0064/O | Other | ALL | Student | Attend lecture |  | 4/24/2026 17:30 | 4/24/2026 19:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
65 | T0065/O | Other | ALL | Student | Attend lecture |  | 4/28/2026 15:30 | 4/28/2026 17:30 | Completed | 1.8 |  | EUR 0,00 |  | Attend lecture.
66 | T0066/O | Other | ALL | Student | Study and train |  | 3/25/2026 0:00 | 4/29/2026 0:00 | Completed | 20 |  | EUR 0,00 |  | Study, read and understand the Level B lecture theory and course materials.
67 | T0067/O | Other | ALL | Student | Attend work meeting |  | 3/31/2026 15:00 | 3/31/2026 15:30 | Completed | 0.5 |  | EUR 0,00 |  | Talk about the work done this week.
68 | T0068/O | Other | ALL | Student | Attend work meeting |  | 2026-07-04 15:00 | 2026-07-04 15:30 | Completed | 0.5 |  | EUR 0,00 |  | Talk about the work done this week.
69 | T0069/O | Other | ALL | Student | Attend work meeting |  | 4/14/2026 15:00 | 4/14/2026 15:30 | Completed | 0.5 |  | EUR 0,00 |  | Talk about the work done this week.
70 | T0070/O | Other | ALL | Student | Attend work meeting |  | 4/21/2026 15:00 | 4/21/2026 15:30 | Completed | 0.5 |  | EUR 0,00 |  | Talk about the work done this week.
71 | T0071/O | Other | ALL | Student | Attend work meeting |  | 4/28/2026 15:00 | 4/28/2026 15:30 | Completed | 0.5 |  | EUR 0,00 |  | Talk about the work done this week.
72 | T0072/D | Development | Student 4 | Developer | Other (Describe) |  | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 100,00 |  | Prepare the Level B analysis report and UML data model required by the auditor (MR-B01), including traceability between the structured requirements and the implemented solution.
73 | T0073/M | Management | Student 4 | Manager | Other (Describe) |  | 2026-07-05 | 2026-08-05 | Completed | 2 |  | EUR 100,00 |  | Validate the analysis decisions and requirement ambiguities with a lecturer and document the confirmed resolutions in the analysis report (AR-B01).
74 | T0074/M | Management | Student 4 | Manager | Make plans |  | 2026-07-05 | 2026-08-05 | Completed | 2 |  | EUR 100,00 |  | Update the Level B planning records with progress tracking, budget estimates, and execution notes as required by the planning report (MR-B02, MR-B03).
75 | T0075/QA/T0035/D | QA | Student 2 | Tester | Test feature formally | T0032/D | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 120,00 |  | Create and execute formal hacking tests for unpublished project access, including guessed URLs, wrong realm, wrong user, wrong action, and tampered navigation attributes, ensuring intrusion alerts or equivalent protection responses.
76 | T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 3 | Tester | Test feature formally | T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 120,00 |  | Record and organise the Level B legal and hacking trace files, converting them into repeatable .legal and .hacking test cases for the formal test suite.
77 | T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 4 | Tester | Test feature formally | T0076/QA/T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 120,00 |  | Replay the Level B formal test suite and review instruction coverage and the test case analyser results, identifying missing legal or hacking test cases where feasible.
78 | T0078/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 5 | Tester | Test feature formally | T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 3 |  | EUR 90,00 |  | Review path coverage, loop cases, and mutation-oriented checks for the Level B test suite, documenting uncovered paths and justified exclusions where applicable.
79 | T0079/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 1 | Tester | Test feature formally | T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 3 |  | EUR 90,00 |  | Check testing variability conditions for Level B, including English/Spanish rendering, simulated clock usage for temporal data, and simulated random seed control for repeatable execution.
80 | T0080/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 2 | Tester | Test feature formally | T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 120,00 |  | Replay the Level B test suite, import tester.trace into Excel, filter resource requests, compute per-feature execution times, and prepare the summary chart required for the performance analysis workflow.
81 | T0081/QA/T0080/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | QA | Student 3 | Tester | Test feature formally | T0080/QA/T0077/QA/T0076/QA/T0045/QA/T0044/QA/T0012/D | 2026-07-05 | 2026-08-05 | Completed | 3 |  | EUR 90,00 |  | Compute descriptive statistics and a 95% confidence interval for the Level B execution times using the performance data gathered from the formal test suite.
82 | T0082/D | Development | Student 1 | Developer | Implement feature |  | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 100,00 |  | Profile the Most Inefficient Request of Level B using the recommended profiling tools and analyse whether the bottleneck is due to software or hardware behaviour.
83 | T0083/D/T0082/D | Development | Student 2 | Developer | Implement feature | T0082/D | 2026-07-05 | 2026-08-05 | Completed | 4 |  | EUR 100,00 |  | Review the Level B queries and refactor them with indices where justified by the performance analysis, documenting the rationale and the affected entities or repositories.
84 | T0084/QA/T0083/D | QA | Student 4 | Tester | Test feature formally | T0083/D | 2026-07-05 | 2026-08-05 | Completed | 3 |  | EUR 90,00 |  | Collect new performance data after the refactoring, perform the hypothesis contrast or Z-test, and document whether the changes produced a statistically significant improvement.
85 | T0085/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-07-05 | 2026-08-05 | Completed | 2 |  | EUR 50,00 |  | Run lint and check-i18n on the Level B codebase, review the findings, and prepare the evidence to support the Lint report.
86 | T0086/M | Management | Student 4 | Manager | Write report |  | 2026-07-05 | 2026-08-05 | Completed | 2 |  | EUR 100,00 |  | Write the Level B analysis report required by the auditor, including the requirement analysis, UML data model, documented ambiguities, confirmed lecturer decisions, and traceability notes.
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O