## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 8720
|  | Actual: | 8002.5
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 4 | Manager | Other (Describe) |  | 2026-01-29 | 2026-01-30 | Completed | 1 | 1 | 50 | 50 | Setup the workgroup.
2 | T0002/M | Management | Student 4 | Manager | Write report |  | 2026-01-29 | 2026-01-30 | Completed | 2 | 2 | 100 | 100 | Prepare a chartering report.
3 | T0003/M | Management | Student 4 | Manager | Make plans |  | 2026-01-29 | 2026-01-31 | Completed | 3 | 4 | 150 | 200 | Instantiate and share a planning document from the planning template provid-ed, and plan on the tasks required to fulfil this deliverable.
4 | T0004/D | Development | ALL | Developer | Other (Describe) |  | 2026-01-30 | 2026-01-31 | Completed | 5 | 5 | 125 | 125 | Install and initialise the workspace.
5 | T0005/M | Management | Student 4 | Manager | Initialise repository |  | 2026-01-31 | 2026-02-01 | Completed | 1 | 4 | 50 | 200 | Initialise the workgroup repository at GitHub.
6 | T0006/D | Development | Student 1 | Developer | Customise the starter |  | 2026-02-02 | 2026-02-03 | Completed | 2 | 1.5 | 50 | 37.5 | Instantiate the starter project “Hello-World” as “Acme-Starters-C”. The corpo-rate colours, banners, logos, and other such stuff is up to the workgroup.
7 | T0007/O | Other | ALL | Student | Study and train |  | 2026-02-02 | 2026-03-20 | Completed | 20 | 20 | 0 | 0 | Study, read and understand the lectures teory.
8 | T0008/O | Other | ALL | Student | Attend work meeting |  | 2026-02-02 15:00 | 2026-02-02 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
9 | T0009/O | Other | ALL | Student | Attend lecture |  | 2026-02-02 15:30 | 2026-02-02 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
10 | T0010/D | Development | Student 2 | Developer | Other (Describe) |  | 2026-02-04 | 2026-02-05 | Completed | 1 | 3 | 25 | 75 | Create the sample data required to create two administrator accounts with cre-dentials “administrator1/administrator1” and “administrator2/administrator2”.
11 | T0011/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-04 | 2026-02-05 | Completed | 3 | 2 | 75 | 50 | Implement the constraints that are sketched in file “Model-CG.ufx”.
12 | T0012/O | Other | ALL | Student | Attend lecture |  | 2026-02-05 15:30 | 2026-02-05 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
13 | T0013/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 9 | 250 | 225 | Implement the data model that is sketched in file “Model-C01.uxf”.
14 | T0014/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 10 | 250 | 250 | Implement the data model that is sketched in file “Model-C02.uxf”.
15 | T0015/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 7 | 250 | 175 | Implement the data model that is sketched in file “Model-C03.uxf”.
16 | T0016/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 9 | 250 | 225 | Implement the data model that is sketched in file “Model-C04.uxf”.
17 | T0017/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-07 | 2026-02-14 | Completed | 10 | 5 | 250 | 125 | Implement the data model that is sketched in file “Model-C05.uxf”.
18 | T0018/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
19 | T0019/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
20 | T0020/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
21 | T0021/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
22 | T0022/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-07 | 2026-03-18 | Completed | 4 | 4 | 100 | 100 | The user interface must be available in English and Spanish. Boolean, moment-related, money-related, and numeric data must be properly internationalised.
23 | T0023/O | Other | ALL | Student | Attend work meeting |  | 2026-02-09 15:00 | 2026-02-09 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
24 | T0024/O | Other | ALL | Student | Attend lecture |  | 2026-02-09 15:30 | 2026-02-09 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
25 | T0025/O | Other | ALL | Student | Attend lecture |  | 2026-02-12 15:30 | 2026-02-12 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
26 | T0026/O | Other | ALL | Student | Attend work meeting |  | 2026-02-16 15:00 | 2026-02-16 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
27 | T0027/O | Other | ALL | Student | Attend lecture |  | 2026-02-16 15:30 | 2026-02-16 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
28 | T0028/O | Other | ALL | Student | Attend lecture |  | 2026-02-19 15:30 | 2026-02-19 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
29 | T0029/QA/T0013/D | QA | Student 1 | Tester | Test feature formally | T0013/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role inventor and credentials “inventori/inventori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
30 | T0030/QA/T0014/D | QA | Student 2 | Tester | Test feature formally | T0014/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role spokesperson and credentials “spokespersoni/spokespersoni”, where “i” ranges in interval one up to three. The last user account must not have any associ-ated data, but the profile data required to create the user account itself and the cor-responding role.
31 | T0031/QA/T0015/D | QA | Student 3 | Tester | Test feature formally | T0015/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role fundraiser and credentials “fundraiseri/fundraiseri”, where “i” ranges in in-terval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
32 | T0032/QA/T0016/D | QA | Student 4 | Tester | Test feature formally | T0016/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 6 | 120 | 180 | Produce sample data to test your requirements. There must be three user accounts with role sponsor and credentials “sponsori/sponsori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the profile data required to create the user account itself and the corresponding role.
33 | T0033/QA/T0017/D | QA | Student 5 | Tester | Test feature formally | T0017/D | 2026-02-22 | 2026-02-23 | Completed | 4 | 4 | 120 | 120 | Produce sample data to test your requirements. There must be three user accounts with role auditor and credentials “auditori/auditori”, where “i” ranges in interval one up to three. The last user account must not have any associated data, but the pro-file data required to create the user account itself and the corresponding role.
34 | T0034/O | Other | ALL | Student | Attend work meeting |  | 2026-02-23 15:00 | 2026-02-23 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
35 | T0035/O | Other | ALL | Student | Attend lecture |  | 2026-02-23 15:30 | 2026-02-23 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
36 | T0036/O | Other | ALL | Student | Attend lecture |  | 2026-02-26 15:30 | 2026-02-26 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
37 | T0037/O | Other | ALL | Student | Attend work meeting |  | 2026-03-02 15:00 | 2026-03-02 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
38 | T0038/O | Other | ALL | Student | Attend lecture |  | 2026-03-02 15:30 | 2026-03-02 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
39 | T0039/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 8 | 200 | 200 | List and display the inventions in the system as long as they have been published. The principal must be able to navigate to their parts and display them. He or she must be able to see the profile of the corresponding inventor.
40 | T0040/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 8 | 200 | 200 | List and display the campaigns in the system as long as they have been published. The principal must be able to navigate to their milestones and display them. He or she must be able to see the profile of the corresponding spokesperson.
41 | T0041/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 7 | 200 | 175 | List and display the strategies in the system as long as they have been published. The principal must be able to navigate to their tactics and display them. He or she must be able to see the profile of the corresponding fundraiser.
42 | T0042/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 5 | 200 | 125 | List and display the sponsorships in the system as long as they have been published. The principal must be able to navigate to their donations and display them. He or she must be able to see the profile of the corresponding sponsor.
43 | T0043/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-05 | 2026-03-09 | Completed | 8 | 6 | 200 | 150 | List and display the audit reports in the system as long as they have been published. The principal must be able to navigate to their audit sections and display them. He or she must be able to see the profile of the corresponding auditor.
44 | T0044/O | Other | ALL | Student | Attend lecture |  | 2026-03-05 15:30 | 2026-03-05 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
45 | T0045/QA/T0017/D | QA | Student 2 | Developer | Test feature informally | T0017/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
46 | T0046/QA/T0039/D | QA | Student 3 | Developer | Test feature informally | T0039/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
47 | T0047/QA/T0040/D | QA | Student 4 | Developer | Test feature informally | T0040/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
48 | T0048/QA/T0041/D | QA | Student 5 | Developer | Test feature informally | T0041/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
49 | T0049/QA/T0042/D | QA | Student 1 | Developer | Test feature informally | T0042/D | 2026-03-09 | 2026-03-10 | Completed | 1 | 1 | 25 | 25 | Test list and display feature.
50 | T0050/O | Other | ALL | Student | Attend work meeting |  | 2026-03-09 15:00 | 2026-03-09 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
51 | T0051/O | Other | ALL | Student | Attend lecture |  | 2026-03-09 15:30 | 2026-03-09 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
52 | T0052/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role inventor as long as he or she does not have that role yet. • Update the corresponding role profile.
53 | T0053/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role spokesperson as long as he or she does not have that role yet. • Update the corresponding role profile.
54 | T0054/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 2 | 100 | 50 | Any authenticated principal must be able to: • Acquire role fundraiser as long as he or she does not have that role yet. • Update the corresponding role profile.
55 | T0055/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 4 | 100 | 100 | Any authenticated principal must be able to: • Acquire role sponsor as long as he or she does not have that role yet. • Update the corresponding role profile.
56 | T0056/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-12 | 2026-03-13 | Completed | 4 | 3 | 100 | 75 | Any authenticated principal must be able to: • Acquire role auditor as long as he or she does not have that role yet. • Update the corresponding role profile.
57 | T0057/O | Other | ALL | Student | Attend lecture |  | 2026-03-12 15:30 | 2026-03-12 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
58 | T0058/QA/T0052/D | QA | Student 2 | Developer | Test feature informally | T0052/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
59 | T0059/QA/T0053/D | QA | Student 3 | Developer | Test feature informally | T0053/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
60 | T0060/QA/T0054/D | QA | Student 4 | Developer | Test feature informally | T0054/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
61 | T0061/QA/T0055/D | QA | Student 5 | Developer | Test feature informally | T0055/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
62 | T0062/QA/T0056/D | QA | Student 1 | Developer | Test feature informally | T0056/D | 2026-03-13 | 2026-03-14 | Completed | 1 | 1 | 25 | 25 | Test adquire and update rol feature.
63 | T0063/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 14 | 8 | 350 | 200 | A principal with role inventor must be able to: • Manage his or her inventions, which involves creating, updating, or deleting them and their corresponding parts.
64 | T0064/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role spokesperson must be able to: • Manage his or her campaigns, which involves creating, updating, or deleting them and their corresponding milestones.
65 | T0065/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role fundraiser must be able to: • Manage his or her strategies, which involves creating, updating, and deleting them and their corresponding tactics.
66 | T0066/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role sponsor must be able to: • Manage his or her sponsorships, which involves creating, updating, or deleting them and their corresponding donations.
67 | T0067/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-14 | 2026-03-16 | Completed | 14 | 10 | 350 | 250 | A principal with role auditor must be able to: • Manage his or her audit reports, which involves creating, updating, or deleting them and their corresponding audit sections.
68 | T0068/QA/T0063/D | QA | Student 2 | Developer | Test feature informally | T0063/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
69 | T0069/QA/T0064/D | QA | Student 3 | Developer | Test feature informally | T0064/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
70 | T0070/QA/T0065/D | QA | Student 4 | Developer | Test feature informally | T0065/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
71 | T0071/QA/T0066/D | QA | Student 5 | Developer | Test feature informally | T0066/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
72 | T0072/QA/T0067/D | QA | Student 1 | Developer | Test feature informally | T0067/D | 2026-03-16 | 2026-03-17 | Completed | 2 | 3 | 50 | 75 | Test CRUD feature.
73 | T0073/O | Other | ALL | Student | Attend work meeting |  | 2026-03-16 15:00 | 2026-03-16 15:30 | Completed | 0.5 | 0.5 | 0 | 0 | Talk about the work done this week.
74 | T0074/O | Other | ALL | Student | Attend lecture |  | 2026-03-16 15:30 | 2026-03-16 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
75 | T0075/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 | 2026-03-12 | Completed | 8 | 4 | 200 | 100 | A principal with role inventor must be able to: • Publish an invention, which prevents it from being updated or deleted. Publishing them implies that their corresponding parts are published automatically, which also prevents them from being updated or deleted.
76 | T0076/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 |  | 200 |  | A principal with role spokesperson must be able to: • Publish a campaign, which prevents it from being updated or deleted. Publishing them implies that their corresponding milestones are published automatically, which also prevents them from being updated or deleted.
77 | T0077/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 4 | 200 | 100 | A principal with role fundraiser must be able to: • Publish a strategy, which prevents it from being updated or deleted. Publishing them implies that their corresponding tactics are published automatically, which al-so prevents them from being updated or deleted.
78 | T0078/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 8 | 200 | 200 | A principal with role sponsor must be able to: • Publish a sponsorship, which prevents it from being updated or deleted. Publishing them implies that their corresponding donations are published automatically, which also prevents them from being updated or deleted.
79 | T0079/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-17 | 2026-03-18 | Completed | 8 | 7 | 200 | 175 | A principal with role auditor must be able to: • Publish an audit report, which prevents it from being updated or deleted. Publish-ing them implies that their corresponding audit sections are published automatical-ly, which also prevents them from being updated or deleted.
80 | T0080/QA/T0075/D | QA | Student 2 | Developer | Test feature informally | T0075/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
81 | T0081/QA/T0076/D | QA | Student 3 | Developer | Test feature informally | T0076/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
82 | T0082/QA/T0077/D | QA | Student 4 | Developer | Test feature informally | T0077/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
83 | T0083/QA/T0078/D | QA | Student 5 | Developer | Test feature informally | T0078/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
84 | T0084/QA/T0079/D | QA | Student 1 | Developer | Test feature informally | T0079/D | 2026-03-18 | 2026-03-18 | Completed | 2 | 3 | 50 | 75 | Test publishing feature.
85 | T0085/QA/T0018/D | QA | Student 2 | Developer | Test feature informally | T0018/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
86 | T0086/QA/T0019/D | QA | Student 3 | Developer | Test feature informally | T0019/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
87 | T0087/QA/T0020/D | QA | Student 4 | Developer | Test feature informally | T0020/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
88 | T0088/QA/T0021/D | QA | Student 5 | Developer | Test feature informally | T0021/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
89 | T0089/QA/T0022/D | QA | Student 1 | Developer | Test feature informally | T0022/D | 2026-03-18 | 2026-03-18 | Completed | 1 | 1 | 25 | 25 | Test languages feature.
90 | T0090/D | Development | Student 2 | Operator | Prepare dep. platf. |  | 2026-03-18 | 2026-03-19 | Completed | 2 | 2 | 60 | 60 | Create deployment configuration.
91 | T0091/D | Development | Student 2 | Operator | Deploy application |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Deploy the application.
92 | T0092/M | Management | Student 2 | Operator | Keep application running | T0091/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 4 | 120 | 120 | Keep it healthy and running.
93 | T0093/D | Development | Student 2 | Operator | Package deliverable |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Package the application for the delivery.
94 | T0094/R/T0093/D | Revision | Student 5 | Tester | Check deliverable | T0093/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 6 | 120 | 180 | Check the deriveables.
95 | T0095/R/T0094/R/T0093/D | Revision | Student 4 | Manager | Supervise task | T0094/R/T0093/D | 2026-03-19 | 2026-03-20 | Completed | 4 | 7 | 200 | 350 | Check the deriveables.
96 | T0096/M | Management | Student 2 | Operator | Upload deliverable |  | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Upload the deriveables to the delivery center.
97 | T0097/R/T0096/M | Revision | Student 5 | Tester | Check task | T0096/M | 2026-03-19 | 2026-03-20 | Completed | 1 | 1 | 30 | 30 | Check the derivery.
98 | T0098/O | Other | ALL | Student | Attend lecture |  | 2026-03-19 15:30 | 2026-03-19 17:20 | Completed | 1.8 | 1.8 | 0 | 0 | Attend lecture.
99
100
101

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 7485
|  | Actual: | 675
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Study and train |  | 2025-03-25 | 2025-04-29 | Completed | 20 |  | 0 |  | Study, read and understand the Level B lecture theory and course materials.
2 | T0002/O | Other | ALL | Student | Attend work meeting |  | 2025-03-31 15:00 | 2025-03-31 15:30 | Completed | 0.5 |  | 0 |  | Talk about the work done this week.
3 | T0003/O | Other | ALL | Student | Attend lecture |  | 2025-03-31 15:30 | 2025-03-31 17:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
4 | T0004/M | Management | Student 4 | Manager | Make plans |  | 2025-04-01 | 2025-04-04 | Completed | 3 | 4 | 150 | 200 | Instantiate and share a planning document from the planning template provided, and plan on the tasks required to fulfil the Level B deliverable.
5 | T0005/M | Management | Student 4 | Manager | Other (Describe) |  | 2025-04-01 | 2025-04-04 | Completed | 1 | 2 | 50 | 100 | Set up the shared workgroup workspace for Level B and ensure all members have access.
6 | T0006/M | Management | Student 4 | Manager | Write report |  | 2025-04-01 | 2025-04-04 | Completed | 2 | 3 | 100 | 150 | Prepare a chartering report for Level B. Review and update the charter and risk analysis for Level B scope.
7 | T0007/M | Management | Student 4 | Manager | Initialise repository |  | 2025-04-01 | 2025-04-04 | Completed | 1 | 1 | 50 | 50 | Initialise the Level B project branch in the workgroup repository at GitHub.
8 | T0008/D | Development | Student 4 | Developer | Other (Describe) |  | 2025-04-01 | 2025-04-04 | Completed | 2 | 3 | 50 | 75 | Prepare the foundations of the analysis report for Level B, including interpretation notes, open issues, and questions that require lecturer confirmation.
9 | T0009/M | Management | ALL | Manager | Other (Describe) |  | 2025-04-01 | 2025-04-04 | Completed | 1 | 1 | 50 | 50 | Ensure that every member understands the scope and goals of Level B and agrees to the common working methodology.
10 | T0010/D | Development | Student 1 | Developer | Customise the starter |  | 2025-04-01 | 2025-04-04 | Completed | 2 | 1 | 50 | 25 | Adapt the starter project from Level C to Level B. Apply required infrastructure changes and update the project name to "Acme-Starters-B".
11 | T0011/D | Development | Student 4 | Developer | Create dev. config. |  | 2025-04-01 | 2025-04-04 | Completed | 1 | 1 | 25 | 25 | Create the sample data required to populate administrator accounts with credentials "administrator1/administrator1" and "administrator2/administrator2" for Level B.
12 | T0012/D | Development | Student 3 | Developer | Implement feature |  | 2025-04-01 | 2025-04-04 | Completed | 3 |  | 75 |  | Implement the model-level constraints for Level B as sketched in file "Model-BG.uxf".
13 | T0013/O | Other | ALL | Student | Attend lecture |  | 2025-04-03 17:30 | 2025-04-03 19:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
14 | T0014/D | Development | Student 1 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 10 |  | 250 |  | Implement the Level B data model as sketched in file "Model-B01.uxf". Covers the manager role entity and profile attributes: position, skills, and executive flag (IR-B01, IR-B02).
15 | T0015/D | Development | Student 2 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 10 |  | 250 |  | Implement the Level B data model as sketched in file "Model-B02.uxf". Covers the project entity with attributes: title, keywords, description, kick-off moment, and close-out moment (IR-B03).
16 | T0016/D | Development | Student 3 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 10 |  | 250 |  | Implement the Level B data model as sketched in file "Model-B03.uxf". Covers project components: inventions, campaigns, and strategies linked to projects (IR-B04).
17 | T0017/D | Development | Student 4 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 10 |  | 250 |  | Implement the Level B data model as sketched in file "Model-B04.uxf". Covers project members: inventors, spokespeople, and fundraisers linked to projects (IR-B05).
18 | T0018/D | Development | Student 5 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 10 |  | 250 |  | Implement the Level B data model as sketched in file "Model-B05.uxf". Covers project publication state, effort computation (IR-B07), and ad banner entity with slogan, target URL, and picture (IR-B08).
19 | T0019/D | Development | Student 1 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 8 |  | 200 |  | Any authenticated principal must be able to acquire role manager (FR-B01) and update the corresponding manager profile, which includes: position, skills, and executive flag (IR-B02).
20 | T0020/D | Development | Student 2 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 8 |  | 200 |  | A manager must be able to create, update, delete, and display his or her projects (FR-B02). Projects include: title, keywords, description, kick-off moment, and close-out moment (IR-B03).
21 | T0021/D | Development | Student 3 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 8 |  | 200 |  | A manager must be able to select and manage project members: inventors, spokespeople, and fundraisers (FR-B03, IR-B05).
22 | T0022/D | Development | Student 4 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 8 |  | 200 |  | Project members must be able to add their inventions, campaigns, and strategies to projects in which they are involved, even when these components are unpublished (FR-B04, IR-B04).
23 | T0023/D | Development | Student 5 | Developer | Implement feature |  | 2025-04-07 | 2025-04-11 | Completed | 8 |  | 200 |  | Any project member must be able to display project data, including unpublished project data, for projects in which they are involved (FR-B05).
24 | T0024/O | Other | ALL | Student | Attend work meeting |  | 2025-04-07 15:00 | 2025-04-07 15:30 | Completed | 0.5 |  | 0 |  | Talk about the work done this week.
25 | T0025/O | Other | ALL | Student | Attend lecture |  | 2025-04-07 15:30 | 2025-04-07 17:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
26 | T0026/O | Other | ALL | Student | Attend lecture |  | 2025-04-10 17:30 | 2025-04-10 19:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
27 | T0027/QA/T0019/D | QA | Student 2 | Developer | Test feature informally | T0019/D | 2025-04-14 | 2025-04-15 | Completed | 1 |  | 25 |  | Test acquire manager role and update manager profile feature.
28 | T0028/QA/T0020/D | QA | Student 3 | Developer | Test feature informally | T0020/D | 2025-04-14 | 2025-04-15 | Completed | 1 |  | 25 |  | Test manager projects CRUD feature.
29 | T0029/QA/T0021/D | QA | Student 4 | Developer | Test feature informally | T0021/D | 2025-04-14 | 2025-04-15 | Completed | 1 |  | 25 |  | Test project members management feature.
30 | T0030/QA/T0022/D | QA | Student 5 | Developer | Test feature informally | T0022/D | 2025-04-14 | 2025-04-15 | Completed | 1 |  | 25 |  | Test project components (add to project) feature.
31 | T0031/QA/T0023/D | QA | Student 1 | Developer | Test feature informally | T0023/D | 2025-04-14 | 2025-04-15 | Completed | 1 |  | 25 |  | Test project member display feature.
32 | T0032/D | Development | Student 1 | Developer | Implement feature |  | 2025-04-14 | 2025-04-18 | Completed | 8 |  | 200 |  | A manager must be able to publish his or her projects only when they include at least one invention (FR-B06, IR-B06). Publishing a project must automatically publish all its components (FR-B07).
33 | T0033/D | Development | Student 2 | Developer | Implement feature |  | 2025-04-14 | 2025-04-18 | Completed | 8 |  | 200 |  | Managers must have dashboards displaying: total projects managed, deviation vs. other managers, and min/max/average/standard deviation of project effort (FR-B08, IR-B07).
34 | T0034/D | Development | Student 3 | Developer | Implement feature |  | 2025-04-14 | 2025-04-18 | Completed | 8 |  | 200 |  | Any sponsor may sponsor any published project by attaching any of his or her published sponsorships (FR-B09). Access control must prevent unauthorised access to unpublished project data by non-members (NFR-B02).
35 | T0035/D | Development | Student 4 | Developer | Implement feature |  | 2025-04-14 | 2025-04-18 | Completed | 8 |  | 200 |  | Any auditor may audit any published project by attaching any of his or her published audit reports (FR-B10). Access control must prevent unauthorised access to unpublished project data by non-members (NFR-B02).
36 | T0036/D | Development | Student 5 | Developer | Implement feature |  | 2025-04-14 | 2025-04-18 | Completed | 8 |  | 200 |  | The administrator must be able to manage ad banners (FR-B11). Ad banners must be shown as little intrusively as possible (NFR-B01). Each banner stores: slogan, target URL, and picture (IR-B08).
37 | T0037/O | Other | ALL | Student | Attend work meeting |  | 2025-04-14 15:00 | 2025-04-14 15:30 | Completed | 0.5 |  | 0 |  | Talk about the work done this week.
38 | T0038/O | Other | ALL | Student | Attend lecture |  | 2025-04-14 15:30 | 2025-04-14 17:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
39 | T0039/O | Other | ALL | Student | Attend lecture |  | 2025-04-17 17:30 | 2025-04-17 19:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
40 | T0040/QA/T0019/D | QA | Student 2 | Developer | Test feature informally | T0019/D | 2025-04-21 | 2025-04-22 | Completed | 1 |  | 25 |  | Test project publication and cascade publish feature.
41 | T0041/QA/T0020/D | QA | Student 3 | Developer | Test feature informally | T0020/D | 2025-04-21 | 2025-04-22 | Completed | 1 |  | 25 |  | Test manager dashboard and effort computation feature.
42 | T0042/QA/T0021/D | QA | Student 4 | Developer | Test feature informally | T0021/D | 2025-04-21 | 2025-04-22 | Completed | 1 |  | 25 |  | Test sponsor attach to published project feature.
43 | T0043/QA/T0022/D | QA | Student 5 | Developer | Test feature informally | T0022/D | 2025-04-21 | 2025-04-22 | Completed | 1 |  | 25 |  | Test auditor attach audit report to published project feature.
44 | T0044/QA/T0023/D | QA | Student 1 | Developer | Test feature informally | T0023/D | 2025-04-21 | 2025-04-22 | Completed | 1 |  | 25 |  | Test ad banners management and rendering feature.
45 | T0045/O | Other | ALL | Student | Attend work meeting |  | 2025-04-21 15:00 | 2025-04-21 15:30 | Completed | 0.5 |  | 0 |  | Talk about the work done this week.
46 | T0046/O | Other | ALL | Student | Attend lecture |  | 2025-04-21 15:30 | 2025-04-21 17:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
47 | T0047/D | Development | Student 1 | Developer | Implement feature |  | 2025-04-22 | 2025-04-24 | Completed | 4 |  | 100 |  | Implement access control to prevent unauthorised access to unpublished project information by non-members (NFR-B02). Validate transactional consistency of project and component publication (NFR-B04).
48 | T0048/D | Development | Student 2 | Developer | Implement feature |  | 2025-04-22 | 2025-04-24 | Completed | 4 |  | 100 |  | Ensure effort computation and dashboard indicators are numerically consistent and reproducible (NFR-B03). Verify formula: sum(active months of components) / number of involved people (IR-B07).
49 | T0049/D | Development | Student 3 | Developer | Implement feature |  | 2025-04-22 | 2025-04-24 | Completed | 4 |  | 100 |  | Implement non-intrusive rendering of ad banners (NFR-B01). Validate that only published sponsorships and audit reports can be attached to published projects (TR-B06).
50 | T0050/O | Other | ALL | Student | Attend lecture |  | 2025-04-24 17:30 | 2025-04-24 19:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
51 | T0051/QA/T0034/D | QA | Student 4 | Developer | Test feature informally | T0034/D | 2025-04-25 | 2025-04-25 | Completed | 1 |  | 25 |  | Test access control and publication transactional consistency.
52 | T0052/QA/T0035/D | QA | Student 5 | Developer | Test feature informally | T0035/D | 2025-04-25 | 2025-04-25 | Completed | 1 |  | 25 |  | Test effort computation numerical consistency.
53 | T0053/QA/T0036/D | QA | Student 1 | Developer | Test feature informally | T0036/D | 2025-04-25 | 2025-04-25 | Completed | 1 |  | 25 |  | Test ad banner rendering and sponsorship/audit attachment constraints.
54 | T0054/QA/T0064/D | QA | Student 1 | Tester | Test feature formally | T0064/D | 2025-04-25 | 2025-04-28 | Completed | 4 |  | 120 |  | Produce sample data to test manager role features (TR-B01). Create at least three manager accounts with credentials "manageri/manageri" where "i" ranges from one to three. The last account must have profile data only.
55 | T0055/QA/T0020/D | QA | Student 2 | Tester | Test feature formally | T0020/D | 2025-04-25 | 2025-04-28 | Completed | 4 |  | 120 |  | Produce sample data with at least three managers and heterogeneous project portfolios (TR-B01, TR-B02). Include projects with mixed publication states and multiple members/components to validate visibility and publication rules.
56 | T0056/QA/T0019/D | QA | Student 3 | Tester | Test feature formally | T0019/D | 2025-04-25 | 2025-04-28 | Completed | 4 |  | 120 |  | Validate precondition: projects cannot be published unless they contain at least one invention (TR-B03). Validate automatic publication cascade from projects to all components (TR-B04).
57 | T0057/QA/T0020/D | QA | Student 4 | Tester | Test feature formally | T0020/D | 2025-04-25 | 2025-04-28 | Completed | 4 |  | 120 |  | Validate effort computation and dashboard statistics with deterministic datasets (TR-B05). Verify min, max, average, and standard deviation indicators are numerically correct.
58 | T0058/QA/T0023/D | QA | Student 5 | Tester | Test feature formally | T0023/D | 2025-04-25 | 2025-04-28 | Completed | 4 |  | 120 |  | Validate that only published sponsorships and audit reports can be attached to published projects (TR-B06). Validate administrator operations and rendering behaviour for ad banners (TR-B07).
59 | T0059/D | Development | Student 2 | Operator | Prepare dep. platf. |  | 2025-04-28 | 2025-04-28 | Completed | 2 |  | 60 |  | Create deployment configuration for Level B application.
60 | T0060/O | Other | ALL | Student | Attend work meeting |  | 2025-04-28 15:00 | 2025-04-28 15:30 | Completed | 0.5 |  | 0 |  | Talk about the work done this week.
61 | T0061/O | Other | ALL | Student | Attend lecture |  | 2025-04-28 15:30 | 2025-04-28 17:30 | Completed | 1.8 |  | 0 |  | Attend lecture.
62 | T0062/D | Development | Student 2 | Operator | Deploy application | T0059/D | 2025-04-29 | 2025-04-29 | Completed | 1 |  | 30 |  | Deploy the Level B application to the target platform.
63 | T0063/M | Management | Student 2 | Operator | Keep application running | T0059/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Monitor and keep the deployed Level B application healthy and running.
64 | T0064/D | Development | Student 2 | Operator | Package deliverable |  | 2025-04-29 | 2025-04-29 | Completed | 1 |  | 30 |  | Package the Level B application and all required deliverables for submission.
65 | T0065/R/T0064/D | Revision | Student 5 | Tester | Check deliverable | T0064/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Check the Level B deliverables against the requirements checklist.
66 | T0066/R/T0064/D | Revision | Student 4 | Manager | Supervise task | T0064/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 200 |  | Supervise the deliverable checking task and approve for submission.
67 | T0067/M | Management | Student 2 | Operator | Upload deliverable | T0066/R/T0064/D | 2025-04-29 | 2025-04-29 | Completed | 1 |  | 30 |  | Upload the Level B deliverables to the delivery centre.
68 | T0068/R/T0067/M | Revision | Student 5 | Tester | Check task | T0067/M | 2025-04-29 | 2025-04-29 | Completed | 1 |  | 30 |  | Verify that the Level B deliverables have been correctly uploaded to the delivery centre.
69 | T0069/M | Management | Student 4 | Manager | Write report |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Write the planning report required by the customer's auditor, documenting the project planning, task breakdown, schedule, and resource allocation for Level B.
70 | T0070/M | Management | Student 4 | Manager | Write report |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Write the Lint report required by the customer's auditor, documenting the results of static code analysis (linting) performed on the Level B codebase.
71 | T0071/M | Management | Student 4 | Manager | Write report |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Write the testing report required by the customer's auditor, documenting the formal testing activities, test cases, results, and coverage for Level B.
72 | T0072/D | Development | Student 4 | Developer | Other (Describe) |  | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 100 |  | Prepare the Level B analysis report and UML data model required by the auditor (MR-B01), including traceability between the structured requirements and the implemented solution.
73 | T0073/M | Management | Student 4 | Manager | Other (Describe) |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Validate the analysis decisions and requirement ambiguities with a lecturer and document the confirmed resolutions in the analysis report (AR-B01).
74 | T0074/M | Management | Student 4 | Manager | Make plans |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Update the Level B planning records with progress tracking, budget estimates, and execution notes as required by the planning report (MR-B02, MR-B03).
75 | T0075/QA/T0035/D | QA | Student 2 | Tester | Test feature formally | T0035/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Create and execute formal hacking tests for unpublished project access, including guessed URLs, wrong realm, wrong user, wrong action, and tampered navigation attributes, ensuring intrusion alerts or equivalent protection responses.
76 | T0076/QA/T0058/QA/T0023/D | QA | Student 3 | Tester | Test feature formally | T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Record and organise the Level B legal and hacking trace files, converting them into repeatable .legal and .hacking test cases for the formal test suite.
77 | T0077/QA/T0076/QA/T0058/QA/T0023/D | QA | Student 4 | Tester | Test feature formally | T0076/QA/T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Replay the Level B formal test suite and review instruction coverage and the test case analyser results, identifying missing legal or hacking test cases where feasible.
78 | T0078/QA/T0077/QA/T0076/QA/T0058/QA/T0023/D | QA | Student 5 | Tester | Test feature formally | T0077/QA/T0076/QA/T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 3 |  | 90 |  | Review path coverage, loop cases, and mutation-oriented checks for the Level B test suite, documenting uncovered paths and justified exclusions where applicable.
79 | T0079/QA/T0077/QA/T0076/QA/T0058/QA/T0023/D | QA | Student 1 | Tester | Test feature formally | T0077/QA/T0076/QA/T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 3 |  | 90 |  | Check testing variability conditions for Level B, including English/Spanish rendering, simulated clock usage for temporal data, and simulated random seed control for repeatable execution.
80 | T0080/QA/T0077/QA/T0076/QA/T0058/QA/T0023/D | QA | Student 2 | Tester | Test feature formally | T0077/QA/T0076/QA/T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 120 |  | Replay the Level B test suite, import tester.trace into Excel, filter resource requests, compute per-feature execution times, and prepare the summary chart required for the performance analysis workflow.
81 | T0081/QA/T0080/QA/T0077/QA/T0076/QA/T0058/QA/T0023/D | QA | Student 3 | Tester | Test feature formally | T0080/QA/T0077/QA/T0076/QA/T0058/QA/T0023/D | 2025-04-29 | 2025-04-29 | Completed | 3 |  | 90 |  | Compute descriptive statistics and a 95% confidence interval for the Level B execution times using the performance data gathered from the formal test suite.
82 | T0082/D | Development | Student 1 | Developer | Implement feature |  | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 100 |  | Profile the Most Inefficient Request of Level B using the recommended profiling tools and analyse whether the bottleneck is due to software or hardware behaviour.
83 | T0083/D | Development | Student 2 | Developer | Implement feature | T0082/D | 2025-04-29 | 2025-04-29 | Completed | 4 |  | 100 |  | Review the Level B queries and refactor them with indices where justified by the performance analysis, documenting the rationale and the affected entities or repositories.
84 | T0084/QA/T0083/D | QA | Student 4 | Tester | Test feature formally | T0083/D | 2025-04-29 | 2025-04-29 | Completed | 3 |  | 90 |  | Collect new performance data after the refactoring, perform the hypothesis contrast or Z-test, and document whether the changes produced a statistically significant improvement.
85 | T0085/D | Development | Student 1 | Developer | Other (Describe) |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 50 |  | Run lint and check-i18n on the Level B codebase, review the findings, and prepare the evidence to support the Lint report.
86 | T0086/M | Management | Student 4 | Manager | Write report |  | 2025-04-29 | 2025-04-29 | Completed | 2 |  | 100 |  | Write the Level B analysis report required by the auditor, including the requirement analysis, UML data model, documented ambiguities, confirmed lecturer decisions, and traceability notes.
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O